## Document Control
DOCUMENT CONTROL
Reference No. | Form A4
Document Title | NIA Gantt Chart for Bagasse Power Projects Template
Document Author | M/S Grontmij
Reviewed by | Management
Approved By | Management
Document Version | 2 | Document Status | FINAL
Date Released | 2014-11-14
File Name | 20141114_NIAGanttBagasse.xlsx
DOCUMENT CHANGE HISTORY
Version | Date | Author | Description
1 | 2014-11-14 | M/S Grontmij | Initial release
1.1 | 2023-03-30 | Anselm Olweny | Inserted Document Control Page

## Sheet1
NOTICE OF INTENDED APPLICATION: BAGASSE (CO-GENERATION)
Gantt chart
Project:
Developer: | Applicant:
A. Field Investigation and Study Items
|  | Start | End | Duration | [1st, 2nd, etc. are months from the ERA permit date of issue) | [11 empty] | Comments
| Activity (Work) | Date |  | Days
[5 empty] | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th
Preparation
ERA permit award
Meetings with financial institutions
Meetings with permitting authorities (DWRM, NEMA, etc.)
DWRM
NEMA
UIA
Uganda Land Commission
Meetings with local stakeholders (council, etc.)
Meetings on power evacuation
UETCL
Local distribution utility
REA
Terms of reference for consultant/engineer for Feasibility Study
Procurement of consultant/engineer for Feasibility Study
Develop quarterly progress reports
Feasibility Study development
Topographical study
Fuel supply study
Geo-technical and Seismic studies
Environmental and Social Impact Assessment
Resettlement Action Plan
Design optimisation
Project optimisation
Basic design
Network studies
Financial and economic analyses
Construction planning
Risk assessment studies
Preparation of Feasibility Study Report
Construction planning
Business Plan development
Draft PPA
B. Completion and Submission of Reports
| Reports | Date(s) |  |  | 1st: Months | Comments
1. Feasibility Study Report
2. Quarterly Progress Reports
3. Environmental & Social Impact Assessment
4. Resettlement Action Plan
5. Permits and Consents
Terms of Reference approval (NEMA)
Environmental approval (NEMA)
Water abstraction permit (DWRM)
Construction Permit (DWRM)
Licence/Concession for use of riverbank (NEMA)
6. License Application