## Document Control
DOCUMENT CONTROL
Reference No. | Form B7
Document Title | QPR for Biomass Project - Construction Phase
Document Author | M/S Grontmij
Reviewed by | Management
Approved By | Management
Document Version | 2 | Document Status | FINAL
Date Released | 2014-11-21
File Name | 20141121_ConstructionPhaseQPRBiomassTemplate.xlsx
DOCUMENT CHANGE HISTORY
Version | Date | Author | Description
1 | 2014-11-21 | M/S Grontmij | Initial release
1.1 | 2023-03-30 | Anselm Olweny | Updated Logo and Inserted Document Control Page

## Qtr1
[Under the provisions of Section 48 of the Electricity Act Cap 145]
BIOMASS
QUARTERLY PROGRESS REPORT FORMAT FOR LICENSED PROJECT DEVELOPERS: CONSTRUCTION
Name of Developer / License Holder
Project Name
License Number
Effective Date of License
Validity of License
Construction Quarterly Progress Report No:
Reporting Period
Overall Project Progress Achieved To-Date (%)
Date of Commencement of Project Construction
Construction Period (Months)
Commission Date

## 1. Key Project Information
1. KEY PROJECT INFORMATION
Project Location
(District, County, Sub-county, Parish, Village)
GPS Coordinates for Power House
Key Project Parameters
Installed Capacity (MWe)
Type/s of fuel
Fuel supply source/s
Amount of fuel in tons/year
Type of process (combustion, thermal gasification, anaerobic gasification, etc.)
Power House type
Type of Boiler
Power Generation Technology
Type of Turbine
Conversion Factor ( from raw material to kWh)
Distribution / Transmission line type
Line Voltage (kV)
Line Length (km)

## 2. Project Summary
2. PROJECT SUMMARY
Table 2-A: Project Progress Summary
Answer the following questions based on the most up-to-date Construction Work Plan, approved by ERA | Data | Remarks/explanation and action
What is the percentage of work completed?
What is the percentage of funding spent?
By how many days is the project
ahead of schedule?
behind schedule?
By how much is the project
within budget?
outside budget?
List any changes made i relation to the originally approved project plan / scope

## 3.1 Project Milestones
3. PROJECT PROGRESS
3.1 Project Milestones & Deliverables Achieved or in Progress
Based on the most up-to-date Construction Work Plan (CWP), provide the information required in the following tables:-
· Table 3‑A: Project milestones and deliverables
· Table 3‑B: Project reporting on progress
· Table 3‑C: Major project tasks and activities to be undertaken in the next quarter
· Table 3‑D: Deliverables and project scope changes
In addition to this, list major milestones and deliverables that were achieved but were not scheduled in the CWP during the reporting period. Indicate the status of each line item and provide an explanation in cases where the variance between planned and actual completion dates is greater than 5%
Guidelines
Major Deliverable | A tangible output of project work, such as project plant designs, penstock and power house construction, etc.
Major Milestone | A key moment that occurs in a project’s life cycle that indicates that a specific stage in the project has been reached.
Planned Start Date | This is the baseline start date provided in the original CWP in the Gantt Chart in the license agreement.
Planned Completion Date | This is the baseline completion date provided in the original CWP in the Gantt Chart in the license agreement.
Explanation of variance | Why the activity was completed late or early.
How other project activities have been or might be impacted.
What actions need to be taken, if any, to bring the project back on track.
Table 3-A: Project Milestones & Deliverables Achieved or in Progress*
Major Deliverable/Milestone & Description | Planned Start Date** | Actual Start Date | Planned Completion Date** | Revised Completion Date | Percentage Complete | Actual Competion Date | Cost to Date (US$ Million) | Status/Variance Explanation/Comment | Material delivered (%)
Performance Bond
Implementation Agreement
Project Management
Securing of finance
Land acquisition
Signature of PPA
Fuel Supply contracts
Procurement
Engineering
E&S consultant
Others
Detailed design
Acquisition of residual Consents and Governmental Authorisations
Implementation of Stakeholder Engagement Plan
Implementation of E&S Management Plan
RAP implementation
Preparations for Financial Close
Civil Works
Procurement - contractor
Access roads construction
Power plant building construction
Commissioning
Power evacuation line
Contact UETCL, distribution company, REA
Procurement
Detailed design
Construction
Commissioning
Equipment
Procurement
Manufacturing of equipment
Fuel handling
Boiler or Digester
Power Generation Equipment, e.g. steam turbine
Flue gas treatment equipment
Generator
Automation and control equipment
Switchyard equipment, e.g. transformers
Shipment
Delivery of equipment
Fuel handling
Boiler or Digester
Power Generation Equipment, e.g. steam turbine
Flue gas treatment equipment
Generator
Automation and control equipment
Switchyard equipment, e.g. transformers
Installation
Commissioning
* The object of this table is to obtain an overview of the developments during the project's construction phase. Please update this table based
on the same table from the previous Quarterly Progress Report. Where there has been no change, the information from the previous quarter shall
be kept in the table.
** Dates according to the time schedule in the license agreement

## 3.2 Project Reporting
3.2 Project Reporting
Guidelines
Status Report | For all activities in progress (started but not completed) a short report (1 - 2 pages) on the progress during the passed quarter shall be enclosed to this Progress Report
Completion Report | After a main activity (e.g. detailed design) has been completed the study report shall be submitted to ERA
Table 3-B: Project Progress
Major Deliverable/Milestone & Description | Status Report on Progress Enclosed | Completion Report Enclosed | Explanation
Performance Bond
Implementation Agreement
Project Management
Securing of finance
Land acquisition
Signature of PPA
Fuel Supply contracts
Procurement
Engineering
E&S consultant
Others
Detailed design
Preparation of Consents and Governmental Authorisations
Implementation of Stakeholder Engagement Plan
Implementation of E&S Management Plan
RAP implementation
Preparations for Financial Close
Civil Works
Procurement - contractor
Access roads construction
Power plant building construction
Commissioning
Power evacuation line
Contact UETCL, distribution company, REA
Procurement
Detailed design
Construction
Commissioning
Equipment
Procurement
Manufacturing of equipment
Fuel handling
Boiler or Digester
Power Generation Equipment, e.g. steam turbine
Flue gas treatment equipment
Generator
Automation and control equipment
Switchyard equipment, e.g. transformers
Shipment
Delivery of equipment
Fuel handling
Boiler or Digester
Power Generation Equipment, e.g. steam turbine
Flue gas treatment equipment
Generator
Automation and control equipment
Switchyard equipment, e.g. transformers
Installation
Commissioning

## 3.3 Major Project Tasks
3.3 Major Project Tasks & Activities to be Undertaken During the Next Reporting Period
Based on the most up-to-date Operational Working Plan (OWP), list in the following table the tasks and activities that will be undertaken in the next reporting period. Provide an explanation for any anticipated variance between the planned completion dates and the actual completion dates that is greater than 5%
Table 3-C: Major Project Tasks & Activities to be Undertaken in the Next Reporting Period
Task/Activity Item & Description | Planned Start Date | Planned Completion Date | Status/ Anticipated Variance Explanation/Mitigation measures for the variance
etc.

## 3.4 Scope Change
3.4 Scope Changes Identified During this Reporting Period
List in the following table any changes above 5% from the original project objectives and deliverables included within the license conditions that have an impact on the project schedule or budget. Items listed should be all scope and deliverable changes identified during this reporting period, including those that may impact the project in later reporting periods.
Guidelines
Description of scope change: | Describe the change, who initiated it and the requirement that triggered the change. ERA shall approve any change more than 5%
Cost Impact: | Indicate if the scope change affects the project cost. Provide the monetary cost associated with the scope change
Schedule Impact: | Indicate if the scope change affects the project schedule. If yes, provide an estimate of the impact on the schedule (in calendar days)
Impact on the design | Indicate how the scope change will impact on the project design.
Explanation: | Explain the impact of the change on the project design, schedule and budget.
Approved by ERA: | ERA shall approve any scope change more than 5%
Table 3-D: Changes in Scope During this Reporting Period
Description of the change in scope | Cost Impact |  | Schedule Impact |  | Explanation of the need for the change in scope and its impact on project design, cost and schedule | Approved by ERA
| Yes/No | Cost (US$ million) | Yes/No | Schedule Change (Days)
etc.

## 4. Safety
4. PERSON SAFETY
Table 4-A: OHS Management on the Project Site During this Reporting Period
Resource type | This Quarter | Total to Date since Construction start | Remarks
Safety training provided |  |  | Indicate the number of staff provided safety training
Safety inspections |  |  | Indicate the number of safety inspections carried out by management
Table 4-B: Person Accidents, Injuries and Fatalities on the Project Site (own staff, contractor and sub-contractor workers)
| Own staff (number) |  | Third party (number) |  | Compensation paid (USD) |  | Report attached
Resource type | This Quarter | Total to Date since Construction start | This Quarter | Total to Date since Construction start | This Quarter | Total to Date since Construction start | Indicate Y (yes) or N (no)
Record of incidents that occurred*
Record of occupational disease that occurred**
Record of occupational injury that occurred***
Record of fatal occupational injury that occurred****
Table 4-C: Development in Own Staff and Third Party Staff over Project Duration
Quarter (Qrt.1, Qrt. 2, …) | Average number of own staff employed over quarter |  | Average number of local staff employed over the quarter |  | Average number of third party employees working on project (consultants, contractor workers, etc.) over the quarter
Qrt. 1
Qrt. 2
Qrt. 3
Qrt. 4
etc.
* "incident" means an unsafe occurrence arising out of or in the course of work where no personal injury is caused, or where personal injury needs only first-aid treatment (The Occupational Safety and Health Act, 2006)
** "occupational disease" means a disease contracted as a result of an exposure to risk factors arising from a work activity (The Occupational Safety and Health Act, 2006)
*** "occupational injury" means an unsafe occurrence arising out of or in the course of work where no personal injury is caused, or where personal injury needs only first-aid treatment (The Occupational Safety and Health Act, 2006)
**** "fatal occupational injury" means occupational injury leading to death (The Occupational Safety and Health Act, 2006)

## 5. Project Issues
5. PROJECT ISSUES / CHALLENGES
An issue is an immediate problem that requires resolution or an important, unanswered question related to the project. Issues can roll in/out as they arise and are dealt with by the Licensee/project team. Issues can be operational, functional, or technical in nature (e.g. user satisfaction/buy-in, process change requirements, training attendance, reporting, deployment, and staff acquisition), and may impact the project’s timeline, resources, and/or quality of deliverables. Unlike a risk, the Licensee/project team can usually resolve an issue.
Guidelines
Issue Description | Identify the issue or state the question
Open/Closed | Indicate whether the issue is open (outstanding) or closed (resolved)
Project Impact | Briefly explain the consequences of the issue, specifying which project activities/deliverables are affected by the issue
Resolution Approach | The specific methods used to resolve the issue. Briefly explain the relevant processes and procedures that will be used to handle the issue
Resolution Date | Identify the date when the responsible party has resolved or plans to resolve the issue
Responsible Party | Identify the party responsible for resolving the issue.
5.1 Project Issues/ Challenges Experienced
List in the following table any problems requiring immediate resolution. This should cover the entire project construction history so continue the same table from the previous Quarterly Progress Report. Items listed should include all open/outstanding issues and those resolved within this reporting period, as well as issues identified during this reporting period that may impact the project in later reporting periods.
Table 5-A : Project Issues/Challenges
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Issue/challenge description | Mark either T -Technical, F - Financial, or E&S - Environmental and Social | Status (open/closed) | Impact of the issue on the project | Resolution approach adopted | Resolution made and date | Responsible Party

## 6. Project Risks
6. PROJECT RISKS
Risks are factors that may cause a failure to meet the project’s objectives. Risks usually relate to future events which may not be under the control of the project team/Licensee and usually cannot be eliminated. Major risks must be mitigated throughout the project lifecycle. Examples of risks include statutory changes, government policy, stakeholder resistance, budget reduction, project size/complexity, project duration, project cost, process change requirements, and contractor reliance. When a risk becomes reality, the factor becomes an issue and at this stage, the Licensee/project management team must formulate a procedure(s) to address and resolve the issue.
Guidelines
Risk Description | Provide a brief description of the risk, highlighting the consequences of the risk, and estimates of timeframes when the management team thinks the risk will affect the project.
Probability of Occurrence | Estimate the likelihood of the risk occurring using the following values:-
· High (very likely)
· Low(remote)
Risk Tolerance Level | Estimate the project’s tolerance for this risk using the following values:
· High (outside the Licensee’s/project team’s control)
· Low(within the project team’s tolerance set for the current phase)
Mitigation Strategy | Describe the Licensee’s / project team’s strategy for curbing the risk, as well as plans for addressing the risk should it become reality.
Assigned Owner | Nominate a party responsible for risk resolution.
6.1 Project Risks Recurring and Identified During this Reporting Period
List in the following table any factors that may cause a failure to meet the project’s objectives. Items listed should include all risks recurring within this reporting period, all risks identified during this reporting period as well as those identified in earlier periods.
Table 6-A : Project Risks this Reporting Period
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Risk Description | Mark either T -Technical, F - Financial, or E&S - Environmental and Social | Probabi-lity of Occur-rence | Risk Tolerance Level | Mitigation Strategy | Responsible Party | Implications
[7 empty] | Costs in US$ | Time in Days

## 7. E&S Management
7. ENVIRONMENTAL AND SOCIAL MANAGEMENT
License holders are requested to submit to ERA an updated version of the original Environmental and Social Management Plan included in the project's Environmental and Social Impact Assessment, as approved by NEMA. This should at least include the following for each mitigation measure: action, level of priority, timing and deadline for implementation, responsible person, indicator of completeness.
License holders are requested to submit to ERA updated versions of the original supporting documents, primarily the Resettlement Action Plan and the Stakeholder Engagement Plan.
Table 7-A: Key Environmental and Social Performance Indicators*
Social
Number of public meetings held to date
Number of participants at meetings to date
Average number of heavy vehicle transports per day to the site
Number of security personnel employed on site
Number of persons requiring resettlement
Number of persons resettled to date
Number of persons affected by economic displacement
Number of persons receiving compensation to date
Environment
Total volume in m3 of waste generated by type and disposal method
Total volume in m3 of hazardous waste generated by type and disposal method
Number of red-listed flora species transported to make way for project
Number of red-listed fauna species transported to make way for project
* the ESPIs shall be adjusted by ERA to reflect the project's activities
License holders are requested to complete the below table based on information from (i) NEMA's EIA Certificate of Approval and (ii) statutory inspections by ERA, by adding additional environmental and social mitigation requirements.
Table 7-B: Additional Environmental and Social Mitigation Measures
Issues / Aspects | Location |  | Actions undertaken to mitigate environmental / social impact | Key verifiable indicators | % complete | Person Responsible | Level of Compliance | Cost Implications in USD
| Description (e.g. power house) | Coordinates
etc.

## 8. Project Financials
8. PROJECT FINANCIAL ASPECTS
Table 8-A : Summary of Project Financials
| Business Plan | Data | Explanations
1) Project Cost
a) Equity (US$ Million )
b) Debt (US$ Million)
c) Total Project Cost(US$ Million)
d) Government /Donor Grant (US$ Million)
2) Sources of Project Funds / Name of Project Sponsors
3) Date of Achievement of Financial Closure |  |  | Submit documentary evidence
4) Funds Spent / Disbursed to-date (US$ Million) |  |  | Submit documentary evidence of disbursement of funds, including but not limited to SWIFT, etc.
5) Funds Utilized in the Current Quarter (US$ Million)
a) Equity drawn to date (US$ Million)
b) Debt drawn to date (US$ Million)
c) Government/Donor grant drawn to date (US$ Million)
6) Funds expected to be utilized during the next quarter (US$ Million)

## 9. Documentation
9. DOCUMENTATION SUBMITTED IN SUPPORT OF THIS REPORTING PERIOD
List in the table all documents submitted as evidence in support of the project activities undertaken in this reporting period. Such evidence may include but not limited to: Copies of Contract(s) between Licensee and Equipment Suppliers, Copies of Contract(s) with Sub-Contractors, Documentary evidence of disbursement of funds (including but not limited to SWIFT), Copies of import-related documentation, etc.
Table 9-A : Documents submitted in support of this quarter’s report
Documents | Date on Submission | Explanations
Implementation Agreement
Tender Documents for Construction
Copy of signed contract between the Licensee and the Contractor(s)
Copy of signed contract(s) between Licensee and Equipment Suppliers
Copy of signed Contract(s) with Sub-Contractors
Construction Work Plan
Detailed Design Drawings
Evidence of disbursement of funds (cheques, bank transfers, swift, invoices, receipts, etc.)
Copies of relevant import-related documentation
Copy of Interconnection and / or wheeling Agreement for the power evacuation line from power house to interconnection point
Financial Close
Evidence of disbursement of funds (cheques, bank transfers, swift, invoices, receipts, etc.)
Copy of Lenders Term Sheet and Loan Agreement with Lender(s)
Construction Insurance
Operation Insurance for the Plant
Project Organization Chart (attach CVs of key supervisory staff if changes have occurred)
Changes in ownership (majority shareholding) of the partner companies
Changes in Directors in the partner companies
Changes in company names and/or registration
Changes in address of the partner companies
Changes in contact person for the plant
Changes in bankers for the loans to the plant
Changes in the operation insurance
Major transactions between the partner companies
Revised project implementation schedule (Operational Work Plan)
Drawings reflecting any changes in designs
Plan for the Operation and Maintenance
Start-up and Test Schedules
Draft Operations Procedure
Final Design Drawings
Environmental Assessment Report
Updated environmental and social management plan / action plan
Updated resettlement action plan
Updated stakeholder engagement plan
Accidents, Injuries and Fatalities reports

## 10.1 Stakeholder Activities
10. STAKEHOLDER DIALOGUE AND CSR ACTIVITIES
10.1: Stakeholder & CSR Activities
Table 10-A: Stakeholder & CSR Activities Already Carried Out
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Activities (e.g. meetings with concerned villagers) | Date carried out | Target Group | Result

## 10.2 Future Stakeholder Act.
10.2: Planned Stakeholder and CSR Activities
Table 10-B: Planned Stakeholder and CSR Activities
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Activities | Date carried out | Target Group | Expected Result

## 11. Photos
11. PHOTO GALLERY OF PROJECT PROGRESS
List photographs of construction progress of works and other major activities carried out during this reporting period.
No. | Description | Location | Coordinates | Date