## Document Control
DOCUMENT CONTROL
Reference No. | Form B2
Document Title | Licence Gantt Chart for Biomass Projects Template
Document Author | M/S Grontmij
Reviewed by | Management
Approved By | Management
Document Version | 2 | Document Status | FINAL
Date Released | 2014-11-21
File Name | 20141121_LicenceGanttChartBiomassTemplate.xlsx
DOCUMENT CHANGE HISTORY
Version | Date | Author | Description
1 | 2014-11-21 | M/S Grontmij | Initial release
1.1 | 2023-03-30 | Anselm Olweny | Inserted Document Control Page

## Sheet1
LICENSE APPLICATION: BIOMASS
Gantt chart
Project:
Developer:
A. Construction and Commissioning Phase (please indicate timing)
Activity (Work) | Start | End | Duration | (1st, 2nd, etc. are months from the date of the issue of ERA License) | [30 empty] | Comments
| Date |  | Days
|  |  |  | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st
ERA License Award, Effective Date
Implementation Agreement
Project Management
Securing of finance
Land acquisition
Signature of PPA
Fuel Supply contracts
Procurement
Engineering
E&S consultant
Others
Detailed design
Preparation of Consents and Governmental Authorisations
Implementation of Stakeholder Engagement Plan
Implementation of E&S Management Plan
RAP implementation
Preparations for Financial Close
Development of quarterly progress reports
Civil works
Procurement - contractor
Access roads construction
Power plant building construction
Commissioning
Power evacuation line
Contact UETCL, distribution company, REA
Procurement
Detailed design
Construction
Commissioning
Equipment
Procurement
Manufacturing of equipment
Fuel handling
Boiler, Gasifier or Digester
Power Generation Equipment, e.g. steam turbine
Flue gas treatment equipment
Generator
Automation and control equipment
Switchyard equipment, e.g. transformers
Shipment
Installation
Commissioning
B. Key Milestones (please indicate timing)
Deliverables | Start | End | Duration | 1st: (1st, 2nd, etc. are months from the date of the issue of ERA License) | Comments
| Date |  | Days
|  |  |  | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st
Quarterly Progress Reports
Financial Close | [34 empty] | Within 180 days
Implementation Agreement | [34 empty] | Not later than Financial Close
Construction Contract/s | [34 empty] | Not later than Financial Close
- Civil Works
- Equipment
- Power Evacuation line
- Others
Construction Start
Evidence of Consents and Title for the required Project Land | [34 empty] | Within 3 months
Planned stakeholder engagement events
Consents and Governmental Authorisations | [34 empty] | Not later than Financial Close
- Design
- Financing
- Construction
- Ownership
- Operation
- Maintenance
All required Permits and Permissions | [34 empty] | Within 12 months
Plan for the Operation and Maintenance | [34 empty] | On or before Commercial Operations Date
Environmental Assessment Report | [34 empty] | Not later than Financial Close
Detailed Design Drawings | [34 empty] | Not later than Financial Close
Start-up and Test Schedule | [34 empty] | Not later than x days before testing
Draft Operations Procedure | [34 empty] | Not later than x days before Commercial Operations
Final Design Drawings | [34 empty] | Not later than on Commercial Operations Date
Deliverables |  |  |  | 1st: (1st, 2nd, etc. are months from the date of the issue of ERA License) | Comments
|  |  |  | 1st | 2nd | 3rd | 4th | 5th | 6th | 7th | 8th | 9th | 10th | 11th | 12th | 13th | 14th | 15th | 16th | 17th | 18th | 19th | 20th | 21st | 22nd | 23rd | 24th | 25th | 26th | 27th | 28th | 29th | 30th | 31st
Testing and Commissioning of the Plant
Commercial Operation of the Plant
Copies of Manufacturers' Specifications and Operation Manuals | [34 empty] | Not later than x days after Commercial Operations Date
Certificate that all Equipment is New and Unused | [34 empty] | Not later than x days after Commercial Operations Date
As Built Drawings and Complete Specifications | [34 empty] | Not later than 3 months after Commercial Operations Date
Report on Final Project Development Costs | [34 empty] | Not later than 180 days after Commercial Operations Date
Quarterly Progress Reports - Operation | [34 empty] | Every Quarter
Environmental Audit (acc. to NEMA) | [34 empty] | 1 year after Commercial Operations Date