## Document Control
DOCUMENT CONTROL
Reference No. | Form B9
Document Title | QPR for Small Hydopower Project - Operation Phase
Document Author | M/S Grontmij
Reviewed by | Management
Approved By | Management
Document Version | 2 | Document Status | FINAL
Date Released | 2014-11-21
File Name | 20141121_OperationPhaseQPRSmallHPPTemplate.xlsx
DOCUMENT CHANGE HISTORY
Version | Date | Author | Description
1 | 2014-11-21 | M/S Grontmij | Initial release
1.1 | 2023-03-30 | Anselm Olweny | Updated Logo and Inserted Document Control Page

## Qtr1
[Under the provisions of Section 48 of the Electricity Act Cap 145]
SMALL HYDROPOWER
QUARTERLY PROGRESS REPORT FORMAT FOR LICENSED PROJECT OPERATOR: OPERATION
Name of Operater / License Holder
Project Name
License Number
Effective Date of License
Validity of License
Operational Quarterly Progress Report No:
Reporting Period
Plant Commission Date
Date of Commencement of Operations
The Report shall be submitted not later than one month after the end of each calendar quarter. The first Report after Commercial Operation of the plant may cover more than three months in order to adapt the schedule to the calendar quarters.

## 1. Plant Information
1. PLANT INFORMATION
Plant Location
(District, County, Sub-county, Parish, Village)
GPS Coordinates for Power House and Weir
River(s)
Key Plant Parameters
Installed Capacity (MW)
Plant Factor (%)
Plant Type (run-of-river or storage)
Design Flow (m3/s)
Gross Head (m)
Net Head (m)
Turbine Type (Francis, Kaplan, etc.)
Length of Headrace (m)
Length of Penstock (m)
Length of Tailrace (m)
Length of Dam/Weir (m)
Height of Dam/Weir (m)
Distribution / Transmission line type
Line Voltage (kV)
Line Length (m)

## 2. KPIs
2. KEY PERFORMANCE INDICATORS
Year:
Table 2-A: Key Performance Indicators
| Performance Level Achieved | [8 empty] | Notes
| Faults |  |  | Planned Shutdowns |  |  | Unplanned Shutdowns
| Hours of interruption due to faults this quarter per generator installed | Accumulated hours of interruption due to faults per year per generator installed | Approved total hours of interruption due to faults per year per generator installed | Hours of interruption due to planned shutdowns this quarter per generator installed | Accumulated hours of interruption due to planned shutdowns per year per generator installed | Approved total hours of interruption due to planned shutdowns per year per generator installed | Hours of interruption due to unplanned shutdowns this quarter per generator installed | Accumulated hours of interruption due to unplanned shutdowns per year per generator installed | Aproved total hours of interruption due to unplanned shutdowns per year per generator installed
Qrt.1
Generator 1
Generator 2
Qrt.2
Generator 1
Generator 2
Qrt.3
Generator 1
Generator 2
Qrt.4
Generator 1
Generator 2
etc.
Total
Table 2-B: Key Environmental and Social Performance Indicators (ERA to select relevant indicators)
Social |  |  | Qrt.1 | Qrt.2 | Qrt.3 | Qrt.4 | Notes
Number of complaints received from public
Number of worker accidents
Number of worker fatalities
Average number of heavy vehicle transports per day to the plant
Number of sensitization iniatives towards local community
Number of CSR activities held
Environment
Total volume (m3) of waste generated by type and disposal method
Total volume (m3) of hazardous waste generated by type and disposal method
Adjust the above to reflect conditions in the NEMA approval

## 3. Financials
3. FINANCIAL & ECONOMIC PERFORMANCE
Year:
Table 3-A : Summary of Project Income and Costs
Million USD
| J | F | M | A | M | J | J | A | S | O | N | D | Year to date | Remarks
1) Income
Sale of energy | [12 empty] | 0
Emission Credit Sales | [12 empty] | 0
Compensation for deemed energy | [12 empty] | 0
GETFiT top-up premium | [12 empty] | 0
Subsidies (Source?) | [12 empty] | 0
Other energy related income | [12 empty] | 0
Total Energy Income | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) Costs
Financing costs - Interest | [12 empty] | 0
Financing costs - Capital payment | [12 empty] | 0
Depreciation | [12 empty] | 0
Insurance costs | [12 empty] | 0
O&M | [12 empty] | 0
Rental lease on land | [12 empty] | 0
Management fee | [12 empty] | 0
Staff costs | [12 empty] | 0
Total Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3) Investments (Details?) | [12 empty] | 0

## 4. Technical
4. TECHNICAL DATA
Table 4-A: Energy Sent Out
| Energy sent out |  |  | Total Energy sent out | Capacity Limit
| Peak | Shoulder | Off-peak
| MWh | MWh | MWh | MWh | MW | MWh
Qrt 1
Generator 1
Generator 2
etc.
Qrt 2
Generator 1
Generator 2
etc.
Qrt 3
Generator 1
Generator 2
etc.
Qrt 4
Generator 1
Generator 2
etc.
Total
Guidelines
Own consumption |  | Consumption only within own land/site with own line(s) not passing another concession
Table 4-B: Energy Generated & Own Consumption
|  | Generated | Sent-out | Island mode | Own consumption
|  | MWh | MWh | MWh | MWh
Qrt. 1
Generator 1
Generator 2
etc.
Qrt 2
Generator 1
Generator 2
etc.
Qrt 3
Generator 1
Generator 2
etc.
Qrt 4
Generator 1
Generator 2
etc.
Total

## 5. Hydrology
5. HYDROLOGICAL DATA
Table 5-A: Hydrological Information
Quarter (Qrt. 1, Qrt. 2, etc.) | River Level at Intake Point | Permitted Average Ecological Flow (DWRM) | Actual Average Ecological Flow | Variation between Permitted and Actual | Dam Level | Permitted Average Discharge (DWRM) | Actual Average Discharge | Variation
| m | m3/s | m3/s | m3/s | m | m3/s | m3/s | m3/s
Qrt. 1
Qrt. 2
Qrt. 3
Qrt. 4
etc
Table 5-B: Hydropower Flow
Quarter (Qrt. 1, Qrt. 2, etc.) | Minimum water flow through HPP | Average water flow through HPP | Maximum water flow through HPP | Spillage
| m3/s | m3/s | m3/s | m3/s
Qrt. 1
Qrt. 2
Qrt. 3
Qrt. 4
etc

## 6. Outages
6. OUTAGES
Table 6-A: Outages this Quarter
| Time loadshed | Energy lost | Explanation
| hrs | MWh
Scheduled outages
Event 1
Event 2
Event 3
Forced outages
Event 1
Event 2
Event 3
Force majeure outages
Incident 1
Incident 2
Incident 3
Caused by grid downtime
Incident 1
Incident 2
Incident 3
Caused by others
Incident 1
Incident 2
Incident 3
Total

## 7. Safety
7. PERSON SAFETY
Table 7-A: OHS Management on the Project Site During this Reporting Period
Resource type | This Quarter | Total to Date since Construction start | Remarks
Safety training provided |  |  | Indicate the number of staff provided safety training
Safety inspections |  |  | Indicate the number of safety inspections carried out by management
Table 7-B: Person Accidents, Injuries and Fatalities on the Plant Site (own staff, contractor and sub-contractor workers)
| Own staff (number) |  | Third party (number) |  | Compensation paid (USD) |  | Report attached
Resource type | This Quarter | Total to Date since Commissioning/During last 5 years | This Quarter | Total to Date since Commissioning/During last 5 years | This Quarter | Total to Date since Commissioning/During last 5 years | Indicate Y (yes) or N (no)
Record of incidents that occurred*
Record of occupational disease that occurred**
Record of occupational injury that occurred***
Record of fatal occupational injury that occurred****
Table 7-C: Development in Own Staff and Third Party Staff Over Period
Quarter (Qrt.1, Qrt. 2, …) | Average number of own staff employed over quarter |  | Average number of local staff employed over the quarter |  | Average number of third party employees working on project (consultants, contractor workers, etc.) over the quarter
Qrt. 1
Qrt. 2
Qrt. 3
Qrt. 4
etc.
* "incident" means an unsafe occurrence arising out of or in the course of work where no personal injury is caused, or where personal injury needs only first-aid treatment (The Occupational Safety and Health Act, 2006)
** "occupational disease" means a disease contracted as a result of an exposure to risk factors arising from a work activity (The Occupational Safety and Health Act, 2006)
*** "occupational injury" means an unsafe occurrence arising out of or in the course of work where no personal injury is caused, or where personal injury needs only first-aid treatment (The Occupational Safety and Health Act, 2006)
**** "fatal occupational injury" means occupational injury leading to death (The Occupational Safety and Health Act, 2006)

## 8. Plant Issues
8. PLANT ISSUES / CHALLENGES
An issue is an immediate problem that requires resolution or an important, unanswered question related to the plant. Issues can roll in/out as they arise and are dealt with by the Licensee/plant management. Issues can be operational, functional, or technical in nature (e.g. user satisfaction/buy-in, process change requirements, training attendance, reporting, deployment, and staff acquisition), and may impact the project’s timeline, resources, and/or quality of deliverables. Unlike a risk, the Licensee/plant management can usually resolve an issue.
Guidelines
Issue Description | Identify the issue or state the question
Status (Not resolved / Resolved) | Indicate whether the issue is open (outstanding) or closed (resolved)
Project Impact | Briefly explain the consequences of the issue, specifying which project activities/deliverables are affected by the issue
Resolution Approach | The specific methods used to resolve the issue. Briefly explain the relevant processes and procedures that will be used to handle the issue
Resolution Date | Identify the date when the responsible party has resolved or plans to resolve the issue
Responsible Party | Identify the party responsible for resolving the issue.
8.1 Plant Issues/ Challenges Experienced
List in the following table any problems requiring immediate resolution. This should cover the entire plant operation history so continue the same table from the previous Quarterly Progress Report. Items listed should include all open/outstanding issues and those resolved within this reporting period, as well as issues identified during this reporting period that may impact the project in later reporting periods.
Table 8-A : Project Issues/Challenges
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Issue/challenge description | Mark either T -Technical, F - Financial, or E&S - Environmental and Social | Status (open/closed) | Impact of the issue on the plant | Resolution approach adopted | Resolution made and date | Responsible Party

## 9. Plant Risks
9. PLANT RISKS
Risks are factors that may cause a failure to meet the plant's objectives. Risks usually relate to future events which may not be under the control of the Licensee/plant management and usually cannot be eliminated. Major risks must be mitigated throughout the plant lifecycle. Examples of risks include statutory changes, government policy, stakeholder resistance, budget reduction, project size/complexity, project duration, project cost, process change requirements, and contractor reliance. When a risk becomes reality, the factor becomes an issue and at this stage, the Licensee/plant management must formulate a procedure(s) to address and resolve the issue.
Guidelines
Risk Description | Provide a brief description of the risk, highlighting the consequences of the risk, and estimates of timeframes when the management team thinks the risk will affect the project.
Probability of Occurrence | Estimate the likelihood of the risk occurring using the following values:-
· High (very likely)
· Low(remote)
Risk Tolerance Level | Estimate the project’s tolerance for this risk using the following values:
· High (outside the Licensee’s/project team’s control)
· Low(within the project team’s tolerance set for the current phase)
Mitigation Strategy | Describe the Licensee’s / project team’s strategy for curbing the risk, as well as plans for addressing the risk should it become reality.
Assigned Owner | Nominate a party responsible for risk resolution.
9.1 Plant Risks Recurring and Identified During this Reporting Period
List in the following table any factors that may cause a failure to meet the project’s objectives. Items listed should include all risks recurring within this reporting period, all risks identified during this reporting period as well as those identified in earlier periods.
Table 9-A : Plant Risks this Reporting Period
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Risk Description | Mark either T -Technical, F - Financial, or E&S - Environmental and Social | Probabi-lity of Occur-rence | Risk Tolerance Level | Mitigation Strategy | Assigned Owner | Implications
Costs in US$

## 10. E&S Management
10. ENVIRONMENTAL AND SOCIAL MANAGEMENT
License holders are requested to submit to ERA an updated version of the original Environmental and Social Management Plan included in the project's Environmental and Social Impact Assessment, as approved by NEMA. This should at least include the following for each mitigation measure: action, level of priority, timing and deadline for implementation, responsible person, indicator of completeness.
License holders are requested to submit to ERA updated versions of the original supporting documents, primarily the Resettlement Action Plan (if still in effect)and the Stakeholder Engagement Plan.
License holders are requested to complete the below table based on information from (i) NEMA's EIA Certificate of Approval and (ii) statutory inspections by ERA.
Table 10-A: Progress in Implementation of the Environmental and Social Mitigation Measures
Issues / Aspects | Location |  | Actions undertaken to mitigate environmental / social impact | Key verifiable indicators | % complete | Person responsible | Level of Compliance | Cost Impli-cations in USD
| Description (e.g. weir, power house, river) | Coordinates
etc.

## 11. Maintenance
11. MAINTENANCE PLAN UPDATES
Table 11-A: Maintenance Plan Updates
Task/Activity Item & Description | Planned Start Date | Planned Completion Date | Outcome
etc.

## 12.1 Stakeholder Activities
12. STAKEHOLDER DIALOGUE AND CSR ACTIVITIES
12.1: Stakeholder and CSR Activities
Table 12-A: Stakeholder & CSR Activities Already Carried Out
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Activities | Date carried out | Target Group (Public, Local Authority, etc.) | Result

## 12.2 Future Stakeholder Act.
12.2: Planned Stakeholder and CSR Activities
Table 12-B: Planned Stakeholder & CSR Activities
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Activities | Date planned | Target Group (Public, Local Authority, etc.) | Expected Result

## 13. Documentation
13. DOCUMENTATION SUBMITTED IN SUPPORT OF THIS REPORTING PERIOD
List in the table all documents submitted as evidence in support of the project activities undertaken in this reporting period. Such evidence may include but not limited to: Copies of Contract(s) between Licensee and Equipment Suppliers, Copies of Contract(s) with Sub-Contractors, Documentary evidence of disbursement of funds (including but not limited to SWIFT), Copies of import-related documentation, etc.
Table 13-A : Documents submitted in support of this quarter’s report
| Date on Submission | Explanations
Organization Chart (attach CVs of new key supervisory staff using ERA CV Format)
Changes in ownership (majority shareholding) of the partner companies
Changes in Directors in the partner companies
Changes in company names and/or registration
Changes in address of the partner companies
Changes in contact person for the plant
Changes in bankers for the loans to the plant
Changes in the operation insurance
Major transactions between the partner companies
Drawings reflecting any changes in design
Updated environmental and social management plan / action plan
Updated resettlement action plan
Updated stakeholder engagement plan
Accidents, Injuries and Fatalities reports
etc.

## 14. Photos
14. PHOTO GALLERY OF PLANT OPERATION
List photographs of major activities carried out during this reporting period. For example environmental and social mitigation measures, CSR activities, general maintenance, etc.
No. | Description | Location | Coordinates | Date