## Document Control
DOCUMENT CONTROL
Reference No. | Form A16
Document Title | QPR for Small Hydropower Project - Permit Phase
Document Author | M/S Grontmij
Reviewed by | Management
Approved By | Management
Document Version | 2 | Document Status | FINAL
Date Released | 2014-11-21
File Name | 20141121_PermitQPRSmallHPPTemplate.xlsx
DOCUMENT CHANGE HISTORY
Version | Date | Author | Description
1 | 2014-11-21 | M/S Grontmij | Initial release
1.1 | 2023-03-30 | Anselm Olweny | Updated Logo and Inserted Document Control Page

## Qtr1
[Under the provisions of Section 48 of the Electricity Act Cap 145]
SMALL HYDROPOWER
QUARTERLY PROGRESS REPORT FORMAT FOR PERMITTED PROJECT DEVELOPERS: PERMIT PHASE
Name of Permit Holder
Project Name
Permit Number
Effective Date of Permit
Validity of Permit
Quarterly Progress Report No.
Reporting Period (quarter number)
Overall Project Progress Achieved To-Date (%)
Date of Commencement of Feasibility Study
Date of Commencement of ESIA study
Date of Commencement of RAP study
Date of Commencement of Business Plan
Feasibility Period (Months)
Finalisation Date

## 1. Key Project Information
1. KEY PROJECT INFORMATION
Project Location
(District, County, Sub-county, Parish, Village)
GPS coordinates (local Ugandan datum)
Name of River(s)
Total Project Land Requirement (ha)
Key Project Parameters
Projected capacity (MWe)
Plant Factor (%)
Project Type (run-of-river or storage)
Expected dimensioning water flow (m3/s)
Source of water flow information (e.g. DWRM)
Projected energy surplus for sale to grid (GWh/yr)

## 2. Summary
2. SUMMARY
Table 2-A: Progress Summary
Answer the following questions based on the most up-to-date Work Plan | Data | Explanation and action
1) Feasibility Study
a) What is the percentage of work completed on the Feasibility Study?
b) What is the percentage of funding spent?
c) By how many days is the Feasibility Study ahead or behind schedule?
d) By how much is the Feasibility Study within or outside budget?
e) List any changes made to the scope of the Feasbility Study.
2) ESIA Study
a) What is the percentage of work completed on the ESIA?
b) By how many days is the ESIA ahead or behind schedule?
3) Resettlement Action Plan
a) What is the percentage of work completed on the RAP?
b) By how many days is the RAP ahead or behind schedule?
4) Business Plan
a) What is the percentage of work completed on the Business Plan?
b) By how many days is the Business Plan ahead or behind schedule?

## 3.1 Milestones
3. PROGRESS
3.1 Milestones & Deliverables Achieved or in Progress
Based on the most up-to-date Work Plan (WP), provide the information required in the following tables:-
· Table 3‑A: Major Activities, Milestones & Deliverables Achieved or in Progress
· Table 3‑B: Major Feasibility Study tasks and activities undertaken in this quarter
· Table 3‑C: Major Project Tasks & Activities to be Undertaken in the Next Reporting Period
In addition to this, list major milestones and deliverables that were achieved but were not scheduled in the WP during the reporting period. Indicate the status of each line item and provide an explanation in cases where the variance between planned and actual completion dates is greater than 5%
Guidelines
Major Deliverable | A tangible output of work, such as preliminary plant designs, penstock and power house construction, etc.
Major Milestone | A key moment that occurs in the Feasibility Study life cycle that indicates that a specific stage has been reached.
Planned Start Date | This is the baseline start date provided in the original Work Plan, the Gantt Chart in the Permit.
Planned Completion Date | This is the baseline finish date provided in the original Work Plan, the Gantt Chart in the Permit.
Explanation of variance | Why the activity was completed late or early.
How other Feasibility Study phase activities have been or might be impacted.
What actions need to be taken, if any, to bring the Feasibility Study back on track.
Table 3-A: Major Activities, Milestones & Deliverables Achieved or in Progress
Major Activities | Planned Start Date | Actual Start Date | Planned Completion Date | Anticipated Completion Date | Percentage Complete* | Actual Completion Date | Explain Variance
1) Preparation
a) Meetings with financial institutions
b) Meetings with permitting authorities:
- DWRM
- NEMA
- Land owners
- Others (specify)
c) Meetings with local stakeholders
d) Meetings on power evacuation:
- UETCL
- Local distribution utility
- REA
e) Terms of reference for consultant/engineer for Feasibility Study
f) NEMA Terms of reference for environmental and social consultant
g) Procurement of consultants/ engineers for Feasibility Study/ESIA/RAP/Business Planning
2) Feasibility Study Development
a) Topographical study
b) Hydrology study
c) Geo-technical and Seismic studies
d) Design optimisation
e) Basic design
f) Network studies
g) Financial and economic analyses
h) Risk assessment studies
i) Preparation of Feasibility Study Report
3) Construction planning
4) Environmental and Social Impact Assessment
5) Resettlement Action Plan
6) Business Plan development
7) Draft PPA
Major Deliverable/Milestone & Description** |  |  |  |  | Status Report on Progress *** (Y/N) | Actual Completion Date | Completion Report submitted? (Y/N)
Feasibility Study Report
Topographical study
Hydrology study
Geotechnical and seismic studies
Design optimisation
Basic design
Network studies
Financial and economic analyses
Risk assessment studies
ESIA Study Report
RAP Study Report
Construction planning
Business Plan
PPA negotiations
Permits and Consents:
- Terms of Reference approval (NEMA)
- Environmental approval (NEMA)
- Water abstraction permit (DWRM)
- Construction permit (DWRM)
- License for use of riverbank (NEMA)
License Application
* When the level of completion on any documentation has reached 100%, the documentation shall be submitted to ERA.
** ERA reserves the right to request drafts of any study/sub-study report as it sees fit, in order to assess progress made. This shall be submitted in soft copy at ERA's request.
*** For all activities in progress (started but not completed) a short (1 - 2 pages) report on progress during the passed quarter.

## 3.2 Tasks Done
3.2 Activities Undertaken During this Reporting Period
List in the following table the tasks and activities that were undertaken in this reporting period. Provide an explanation for any anticipated variance between the planned completion dates and the actual completion dates that is greater than 5%
Table 3-B: Major Feasibility Study Tasks and Activities Undertaken in this Quarter
Task/Activity Item & Description | Planned Start Date | Planned Completion Date | Explain Variance
1. Feasibility Study
etc.
2. ESIA
etc.
3. RAP
etc.
4. Business Plan
etc.

## 3.3 Future Tasks
3.3 Activities to be Undertaken During the Next Reporting Period
Based on the most up-to-date Work Plan, list in the following table the tasks and activities that will be undertaken in the next reporting period. Provide an explanation for any anticipated variance between the planned completion dates and the actual completion dates that is greater than 5%
Table 3-C: Major Project Tasks & Activities to be Undertaken in the Next Reporting Period
Task/Activity Item & Description | Planned Start Date | Planned Completion Date | Explain Variance
1. Feasibility Study
etc.
2. ESIA
etc.
3. RAP
etc.
4. Business Plan
etc.

## 4. Issues & Risks
4. ISSUES / RISKS FOR PERMIT PHASE
An issue is an immediate problem that requires resolution or an important, unanswered question related to the project. Issues can roll in/out as they arise and are dealt with by the Feasibility Study team. Issues can be operational, functional, or technical in nature (e.g. user satisfaction/buy-in, process change requirements, training attendance, reporting, deployment, and staff acquisition), and may impact the Feasibility Study timeline, resources, and/or quality of deliverables. Unlike a risk, the Permit holder/project team can usually resolve an issue.
Risks are factors that may cause a failure to develop the Feasibility Study. Risks usually relate to future events which may not be under the control of the project team/Permit holder and usually cannot be eliminated. Major risks must be mitigated throughout the project lifecycle. Examples of risks include statutory changes, government policy, stakeholder resistance, budget reduction, project size/complexity, project duration, project cost, process change requirements, and consultant reliance. When a risk becomes reality, the factor becomes an issue and at this stage, the Permit holder/project team must formulate a procedure(s) to address and resolve the issue.
Guidelines
Description | Provide a brief description of the issue/risk, highlighting the consequences, and estimates of timeframes when the management team thinks the issue/risk will affect the development of the Feasibility Study.
Probability of Occurrence | Estimate the likelihood of the issue/risk occurring using the following values:-
· High (very likely)
· Low (remote)
Tolerance Level | Estimate the tolerance using the following values:
· High (outside the Permit holder's/project team’s control)
· Low (within the Permit holder's/project team’s tolerance set for the current phase)
Mitigation Strategy | Describe the Permit holder's/project team’s strategy for managing the issue/risk, as well as plans for addressing it should it become reality.
Assigned Owner | Nominate a party responsible for resolution.
4.1 Issues/ Risks Experienced
List in the following table any problems requiring immediate resolution. This should cover the entire Feasibility Study phase so continue the same table from the previous Quarterly Progress Report. Items listed should include all open/outstanding issues and risks, those resolved within this reporting period, as well as issues identified during this reporting period that may impact the project in later reporting periods.
Table 4-A : Issues/Risks this Reporting Period
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Description | Mark either T -Technical, F - Financial, or E&S - Environmental and Social | Probability of Occurrence | Tolerance Level | Mitigation Strategy | Assigned Owner | Implications
[7 empty] | Costs in US$ | Time in Days

## 5. Documentation
5. DOCUMENTATION SUBMITTED IN SUPPORT OF THIS REPORTING PERIOD
List in the table all documents submitted as evidence in support of the project activities undertaken in this reporting period. Such evidence may include but not limited to: Copies of Contract(s) between Licensee and Equipment Suppliers, Copies of Contract(s) with Sub-Contractors, Documentary evidence of disbursement of funds (including but not limited to SWIFT), Copies of import-related documentation, etc.
Table 5-A : Documents submitted in support of this quarter’s report*
| Date of Submission | Explanations
Copy of signed contract between the Permit holder and the Technical consultant(s)
Copy of Terms of Reference for E&S consultant submitted to NEMA
Copy of signed contract between the Permit holder and the Environmental and Social consultant(s)
Project Organization Chart (attach CVs of key technical and supervisory staff, including Project Manager: only if changes in staffing)
Changes in ownership of the partner companies
Changes in company names and/or registration
Changes in address of the partner companies
Changes in contact person for the project
Changes in bankers for the loan to the plant
Major transactions between partner companies
Feasibility Study Report
ESIA Study Report
RAP Study Report
Permits and Consents:
- Terms of Reference approval (NEMA)
- Environmental approval (NEMA)
- Water abstraction permit (DWRM)
- Construction permit (DWRM)
- License for use of riverbank (NEMA)
- Other (please specify)
* In accordance with the permit conditions
** Note that ERA will refer to the Gantt chart included with the final permit decision to ascertain which documents are scheduled to be submitted

## 6.1 Stakeholder Activities
6. STAKEHOLDER DIALOGUE AND CSR ACTIVITIES
6.1: Stakeholder & CSR Activities
List in the following table any stakeholder dialogue and CSR activities that have been carried out. This should cover the entire Feasibility Study phase so continue the same table from the previous Quarterly Progress Report.
Table 6-A: Stakeholder & CSR Activities Already Carried Out
Quarter incurred (Qrt 1, Qrt. 2, etc.) | Activities | Date carried out | Target Group | Result
E.g. community meetings, local council, NEMA, DWRM, etc.

## 6.2 Future Stakeholder Act.
6.2: Planned Stakeholder & CSR Activities
List in the following table any planned stakeholder dialogue and CSR activities. This should cover the entire Feasibility Study phase so continue the same table from the previous Quarterly Progress Report.
Table 6-B: Planned Stakeholder & CSR Activities
Quarter planned (Qrt 1, Qrt. 2, etc.) | Activities | Date to be carried out | Target Group | Expected Result
E.g. community meetings, local council, NEMA, DWRM, etc.

## 7. Photos
7. PHOTO GALLERY OF FEASIBILITY-RELATED ACTIVITIES
List photographs associated with progress made, and issues/risks identified as well as stakeholder dialogue and CSR activities.
Table 7-A: Photo List
No. | Description | Location | GPS Coordinates | Date